## Summary
TRA Prototype Audit — Findings Summary
Audit date: | 2026-07-13
Auditor: | Super Z (multi-agent, 4-track parallel audit)
Repo: | github.com/nordeim/Translation-Runtime-Architecture @ HEAD
Severity lexicon: | TRA-SPECIFICATION.md §7 (BLOCKING / WARNING / INFO)
Severity | Count
BLOCKING | 11
WARNING | 22
INFO | 2
TOTAL | 35
By Track
Track | Name | BLOCKING | WARNING | INFO | TOTAL
A | Spec Conformance | 5 | 5 | 0 | 10
B | Code Quality & Security | 1 | 8 | 0 | 9
C | Doc Consistency | 2 | 6 | 0 | 8
D | Test Suite | 3 | 3 | 2 | 8
By Category
Category | BLOCKING | WARNING | INFO | TOTAL
Spec Conformance | 5 | 5 | 0 | 10
Code Quality | 1 | 7 | 0 | 8
Security | 0 | 1 | 0 | 1
Doc Consistency | 2 | 6 | 0 | 8
Test Suite | 3 | 3 | 2 | 8

## Findings
ID | Severity | Track | Category | Title | Evidence (file:line) | Detail | Suggested Fix
TRA-001 | BLOCKING | A | Spec Conformance / ISA Contract | TRANSLATE_SEGMENT receives whole document, not a segment | kernel.py:186; TRA-ISA-REFERENCE.md:48-49; cache.py:12-13 | The ISA contract (TRA-ISA-REFERENCE.md §TRANSLATE_SEGMENT) mandates that the instruction operates on 'a specific source segment (sentence, list item, or table cell)'. The kernel passes the entire source markdown as one segment (kernel.py:186 `translate_segment(src, ...)`). Consequences: cache keys are per-document (violating cache.py:12-13 'never a whole document'), RepairAttempt.segment_index is always 0, L4 line-by-line trace uses substring heuristic rather than structural mapping, and is_no_translate_zone markers on code blocks are never consulted (S-03 violated). The kernel.py:184 inline comment admits 'Segment granularity is wired in Phase 3' — Phase 3 never landed. | Refactor _execute_translation to iterate StructuralMap leaf nodes (paragraphs, list items, table cells, headings), call translate_segment per leaf, and reassemble via the structural map. Skip nodes where is_no_translate_zone=True.
TRA-002 | BLOCKING | A | Spec Conformance / Module Extension | Module registry is the sanctioned extension point but kernel bypasses it | kernel.py:43,106; isa.py:50,54; CLAUDE.md:40; SKILL.md:151-163 | CLAUDE.md and SKILL.md §6 document the module registry as the 'only sanctioned path' for new language bridges: `registry = build_default_registry(); registry.register(my_module.as_interface())`. In production code, the kernel hard-codes `ZHENModule()` directly (kernel.py:43 import, kernel.py:106 instantiation; isa.py:50,54 same pattern). Grep confirms ZERO production callers of build_default_registry or registry_for_language_pair. A user following SKILL.md §6 verbatim will find their registered module is NOT used by `tra_cli.py translate`. | Replace the hard-coded `ZHENModule()` in kernel.py and isa.py with a registry lookup: `module = registry_for_language_pair(config.language_pair)`. Inject the module via constructor instead of module-level singleton.
TRA-003 | BLOCKING | A | Spec Conformance / Critical Invariant | repair_segment does not enforce surgical invariant at function boundary | isa.py:515-519; TRA-ISA-REFERENCE.md:79; TRA-SPECIFICATION.md:83 | The spec mandates 'Repair must resolve the specific violation without introducing new ones' (TRA-ISA-REFERENCE.md:79, mirrored in TRA-SPECIFICATION.md:83, CLAUDE.md:79, AGENTS.md:33, README.md:123). The code (isa.py:515-519) only raises Unrecoverable when `new_blocking and attempt >= max_retries`. At attempt=1 with max_retries=3, a repair that introduces new BLOCKING returns silently with resolved=False. Empirically confirmed: calling repair_segment(target='成立 Valid', attempt=1, max_retries=3) returns 'Confirmed Valid' (containing the forbidden drift target 'Valid') without raising. The kernel's _repair_loop catches this by re-queuing, but a direct caller receives broken output with no exception. | Remove the `attempt >= max_retries` guard from the new-BLOCKING check. Raise Unrecoverable unconditionally on any new BLOCKING, regardless of attempt number. Add a regression test that calls repair_segment directly with attempt=1 and asserts the raise.
TRA-004 | BLOCKING | A | Spec Conformance / Exception Recovery | 4 of 5 TRA-EXCEPTION recovery procedures are unreachable | isa.py:84 (BrokenMarkdown raised, kernel.py:129 not caught); recovery.py:154 | Spec §6 mandates deterministic recovery for all 5 TRA-EXCEPTION types. Grep across tra/ for `raise UnknownTerm¦raise CertaintyConflict¦raise EntityAmbiguity` returns ZERO hits — these exception classes exist but are never raised in production code paths. BrokenMarkdown IS raised by analyze_document (isa.py:84) but kernel.py:129 calls analyze_document with NO try/except, so a malformed source crashes the kernel with no EXCEPTION_HANDLER invocation. Only GlossaryConflict (build_glossary) and Unrecoverable (repair_segment) reach route_exception. The recovery.py dispatcher and 3 of its 5 handlers are dead code. | Wrap each ISA call in kernel.run() with try/except TRAException and route through self._recover(). Add UNKNOWN_TERM / CERTAINTY_CONFLICT / ENTITY_AMBIGUITY raise sites in the relevant ISA instructions (translate_segment for UNKNOWN_TERM, verify_output for CERTAINTY_CONFLICT, build_entity_table for ENTITY_AMBIGUITY).
TRA-005 | BLOCKING | A | Spec Conformance / L3 Gate | kernel.run() does not enforce the L3 zero-BLOCKING gate | kernel.py:157; tra_cli.py:106-120; TRA-CONFORMANCE-GUIDE.md:51 | Per TRA-CONFORMANCE-GUIDE.md:51, 'If [BLOCKING diagnostics are] present, certification is denied.' The kernel's run() method (kernel.py:157) returns the target unconditionally, even when _repair_loop exhausts max_retries with BLOCKING diagnostics still present. The CLI (tra_cli.py:106-120) only prints a warning. Only validate.py and benchmark.py enforce zero-BLOCKING. A user running `tra_cli.py translate --level L3` on a document that produces BLOCKING diagnostics receives a 'translated' output and no error signal. | After _repair_loop, re-run verify_output. If any BLOCKING remains, raise a TRAException (e.g., ConformanceFailure) that the CLI catches and exits 1 with a clear message. Document that `translate` is a best-effort runner and `validate` is the certification gate.
TRA-006 | WARNING | A | Spec Conformance / Policy Engine | PolicyResolver is scaffolding — never invoked in production | policy.py:13 (definition); test_phase0.py:23 (only test import) | The 6-priority PolicyResolver exists but is never called by the kernel or ISA. Grep confirms only the definition and a test import. The policy_stack is consulted only for cache-key hashing (cache.py:65), never for arbitration. verify_output has no Factual-Integrity check (strings like '<60ms', '96-core', '<5MB' aren't entities and aren't verified), no structural check beyond heading count, no fluency check. The spec's scope rules (code blocks: only Fluency relaxable; headings: Factual beats Structural) are not implemented. | Wire PolicyResolver into verify_output and repair_segment. At minimum, implement the Factual Integrity check (numbers/units/versions preservation beyond entity extraction) and the scope rules for code blocks vs headings.
TRA-007 | WARNING | A | Spec Conformance / Kernel Transitions | Kernel transitions fire BEFORE ISA completion, not after | kernel.py:127-157; CLAUDE.md:19; TRA-SPECIFICATION.md §2.1 | CLAUDE.md:19 claims 'transitions only on successful ISA completion'. The kernel calls `self._transition(KernelState.ANALYZE_DOCUMENT)` at kernel.py:128 BEFORE calling `analyze_document(...)` at kernel.py:129. If the ISA raises, the state has already advanced. The spec §2.1 state diagram includes an EXCEPTION_HANDLER state for failed ISA calls — the kernel does not model this state at all. | Move each `self._transition(...)` call to AFTER the corresponding ISA call returns successfully. Add a KernelState.EXCEPTION_HANDLER state (or route via _recover) for the failure path. Update CLAUDE.md:19 to match the implementation if you choose not to fix the code.
TRA-008 | WARNING | A | Spec Conformance / Structural Integrity | Anchor rewrite_links defined but never called — S-06 dead in production | anchor.py:rewrite_links; kernel.py:142-156 (no rewrite call) | AnchorRegistry.rewrite_links is implemented and unit-tested (test_anchor.py S-06 case), but the kernel's _execute_translation never calls it. Translated headings produce new slugs that don't match internal `#anchor` links in the rest of the document. The structural integrity check in verify_output only counts headings — it does not verify link integrity. | After reassembling translated segments, call `registry.rewrite_links(translated_ast)` before returning the target. Add a verify_output check that every internal `#link` resolves to a heading slug in the target.
TRA-009 | WARNING | A | Spec Conformance / Terminological Consistency | Terminology violations classified as WARNING, not BLOCKING | isa.py:429 | When a source glossary term leaks into the target untranslated, verify_output (isa.py:429) emits a WARNING. Per Spec §5, Terminological Consistency is Priority 4 — higher than Fluency (6) but lower than Entity (3). The spec does not mandate BLOCKING for terminology drift, but the L3 gate's 'zero BLOCKING' criterion means terminology drift alone never blocks certification. This may be intentional but should be documented. | Either escalate terminology violations to BLOCKING at L3+ (stricter than spec, but safer), or document the WARNING classification explicitly in CLAUDE.md and TRA-CONFORMANCE-GUIDE.md.
TRA-010 | WARNING | A | Spec Conformance / Memory Model | Memory model immutability claims unenforced | memory.py:172 (RuntimeContext not frozen); config.py:23 (BootstrapConfig not frozen) | Spec §4 describes Immutable Config (read-only) and Audit Memory (append-only). In code, BootstrapConfig is a plain Pydantic BaseModel (not frozen=True). The CLI directly mutates it (tra_cli.py:87-89 sets level/lang on the config object). AuditTrail is append-only by API convention but nothing prevents a stray `.records.clear()` call. count_blocking is a stub returning 0 (see TRA-016). | Add `model_config = ConfigDict(frozen=True)` to BootstrapConfig. Make AuditTrail.records a tuple or use a frozen list wrapper. Implement or remove count_blocking.
TRA-011 | BLOCKING | B | Code Quality / Cache Invalidation | cache-clear --pattern is a silent no-op (diskcache.delete takes literal key) | cache.py:107-115; tra_cli.py:123-132 | TranslationCache.invalidate(pattern) calls `self._cache.delete(pattern)`. diskcache's delete() takes a LITERAL key, not a glob. Empirically confirmed: invalidate('test*') on a cache with 3 entries deletes 0 (3→3); the literal-key invalidate works (3→2). The CLI (tra_cli.py:130) then prints 'Cache invalidated: <pattern>' unconditionally — lying to the user. A user who runs `tra cache-clear --pattern 'translation:*'` to invalidate stale entries believes they were cleared; they weren't. This could serve stale translations indefinitely. | Implement glob via `for key in self._cache.iterkeys(): if fnmatch(key, pattern): self._cache.delete(key)`. Alternatively, drop --pattern and only support `cache-clear` (full clear). Update the CLI to print the actual count deleted.
TRA-012 | WARNING | B | Code Quality / Input Sanitization | _sanitize_input bypassed at validate and benchmark boundaries | kernel.py:75-90 (regex); validate.py:71-72; benchmark.py:102-104 | The _sanitize_input regex (kernel.py:78-80) correctly strips null bytes, C0 control chars, DEL, Unicode bidi overrides (\u202a-\u202e), and BOM (\ufeff). It is only called from TRAKernel.run() (kernel.py:125). validate_translation (validate.py:71-72) calls analyze_document(source) directly with no sanitization. BenchmarkRunner.run_case (benchmark.py:102-104) re-verifies via analyze_document(case.source) unsanitized. A malicious candidate file with bidi-override characters could be processed by `tra validate` without sanitization, potentially confusing auditors who inspect the rendered output. | Move _sanitize_input to a shared utility (e.g., utils.py or a new security.py). Call it at the top of validate_translation, analyze_document, and the benchmark re-verify block. Add a test that confirms bidi-override characters are stripped at every entry point.
TRA-013 | WARNING | B | Code Quality / Reproducibility | Audit trail is NOT byte-reproducible (uuid4 + datetime.now) | diagnostics.py:40 (uuid4); diagnostics.py:58 (datetime.now(UTC)) | Empirically confirmed: two runs of identical source produce identical target text, identical cache.db, identical glossary/entity/smap/style/exec_log/repair_history — but DIFFERENT audit_trace.jsonl. Diff shows every record differs in `timestamp`, and records 1-3 also differ in all evidence_chain IDs (random ev_<uuid4.hex[:12]>). For L4 forensic audits (legal/security per TRA-CONFORMANCE-GUIDE.md), this means you cannot cryptographically prove 'this audit trail corresponds to this output' by hashing the trail. The R-01 regression test (test_benchmark.py:65-71) only checks output equality, not audit-trail equality. | Make evidence IDs deterministic: `ev_{sha256(content)[:12]}` instead of uuid4. Replace datetime.now(UTC) with a deterministic timestamp derived from the source hash, or accept an optional `timestamp` parameter. Add a test asserting audit-trail byte-equality across two runs of the same input.
TRA-014 | WARNING | B | Security / Path Traversal | No path-traversal protection on config-supplied paths | config.py:23-55; kernel.py:240-312 (mkdir + write) | BootstrapConfig.from_yaml accepts compilation_dir, audit_trace, cache_directory from config.yaml with no sanitization. A malicious config with `compilation_dir: '../../../etc'`, `audit_trace: '/tmp/evil.jsonl'`, `cache_directory: '/var/tmp/evil-cache'` is accepted and the kernel writes 6-8 files there. AuditTrail.flush() calls mkdir(parents=True) on arbitrary paths. Acceptable for a trusted-config prototype; unacceptable for production. | Resolve all config paths against a project root. Reject paths containing `..` or absolute paths outside the project root. Add a test that confirms a malicious config is rejected.
TRA-015 | WARNING | B | Code Quality / Audit Trail | Double audit record on LLM graceful degradation | isa.py:316-346 | When llm_translate raises, isa.py:322-330 appends a TRANSLATE_SEGMENT record with artifact_snapshot={'degraded': True, 'reason': ...}. The code then FALLS THROUGH to isa.py:334-346, appending ANOTHER TRANSLATE_SEGMENT record (with evidence_chain, no degraded flag). Empirically verified: degraded translation produces 2 records — Record 0 {'degraded': True, ...}, Record 1 {}. An L3 auditor inspecting the LAST TRANSLATE_SEGMENT per segment misses the degradation. The existing test test_graceful_degradation_on_llm_failure uses any(...) so it passes but doesn't catch the double-record issue. | Add a `return` statement after the degradation-notice audit.append, OR merge the degraded flag into the single normal-path record. Update the test to assert exactly one TRANSLATE_SEGMENT record per segment.
TRA-016 | WARNING | B | Code Quality / Dead Code | AuditTrail.count_blocking is a stub returning 0 unconditionally | diagnostics.py:159-166 | The method name suggests it counts BLOCKING diagnostics in the audit trail. The implementation returns 0 unconditionally with a comment 'hook for VERIFY to populate'. Zero callers in production or tests. If a future contributor trusts the method name, they will get a false L3 PASS. Real counting lives in reporting.summarize_audit and validate.ValidationReport. | Either implement count_blocking by scanning the audit trail for records with 'BLOCKING' in flags_raised, or delete the method and direct readers to reporting.summarize_audit.
TRA-017 | WARNING | B | Code Quality / Dependency Hygiene | 5 unused dependencies inflate install footprint (~50+ transitive packages) | pyproject.toml:10-21; grep across tra/ for imports | litellm (>=1.49), structlog (>=24.1), pydantic-settings (>=2.3), mdit-py-plugins (>=0.4), and black (>=24.4, dev) are listed but never imported. litellm alone pulls ~30 transitive deps (openai, tiktoken, tokenizers, huggingface-hub, httpx, aiohttp, jinja2, jsonschema, ...). The LLM seam is wired as a caller-supplied Callable, so litellm is not actually needed at runtime. pytest-asyncio (dev) is also unused (asyncio_mode=auto set but zero async tests). Total install: ~50+ packages, hundreds of MB, for a rule-based prototype. | Move litellm to optional-dependencies.llm. Drop pydantic-settings, mdit-py-plugins, structlog, black, pytest-asyncio from the manifest. Add a 'Dependency hygiene' bullet to CLAUDE.md Known gaps.
TRA-018 | WARNING | B | Code Quality / Pydantic v2 | Immutability claims on Entity and BootstrapConfig unenforced (no frozen=True) | memory.py:154 (Entity); config.py:23 (BootstrapConfig) | Entity is documented as 'an immutable identifier isolated from natural-language translation' but is a plain BaseModel with mutable=True default. BootstrapConfig is described as the 'Immutable Config (read-only)' memory segment but is also a plain BaseModel. The CLI (tra_cli.py:87-89) directly mutates BootstrapConfig. Zero ConfigDict(frozen=True) anywhere in the codebase. Zero Field constraints (min_length, pattern, ge, le) on any model. | Add `model_config = ConfigDict(frozen=True)` to Entity, GlossaryEntry, ForbiddenMapping, and BootstrapConfig. For RuntimeContext (which must be mutable), leave unfrozen but document why. Add Field constraints where applicable (e.g., ConformanceLevel enum, non-empty source strings).
TRA-019 | WARNING | B | Code Quality / Assert Usage | 2 runtime asserts in kernel.py stripped under python -O | kernel.py:130-131 | kernel.py:130-131 uses `assert self.ctx.document_profile is not None` and `assert self.ctx.structural_map is not None` for runtime validation. Python asserts are stripped when the interpreter runs with -O (optimized mode). A production deployment using -O would silently skip these checks. The spec's 'never skip instructions' principle suggests these should be hard raises. | Replace `assert x is not None` with `if x is None: raise TRAException(...)`. Reserve assert for invariants that are truly impossible to violate.
TRA-020 | BLOCKING | C | Doc Consistency / Known Gaps | CLAUDE.md 'Known gaps (honest, not yet addressed)' lists only 3 of ~16 material gaps | CLAUDE.md:42-46 | CLAUDE.md:42-46 labels the list 'Known gaps (honest, not yet addressed)' but enumerates only: structlog unused, no asyncio parallelism, no cross-run glossary/entity caching. At least 16 material gaps exist (TRA-001 through TRA-019 in this audit, plus Phase 7 items). The word 'honest' is itself misleading when the list omits the most material gaps (segment-level granularity, registry bypass, repair-attempt-1, exception recovery, L3 gate not enforced in translate, count_blocking stub, cache-clear no-op, etc.). | Replace the 3-bullet list with a numbered list of all known material gaps (this audit's TRA-001 through TRA-019 is a starting point). Drop the word 'honest' or make it true. Cross-reference each gap to its finding ID for traceability.
TRA-021 | BLOCKING | C | Doc Consistency / Status Header | tra-prototype/README.md says 'Phase 0-5' and 'Phase 6 pending' — both false | tra-prototype/README.md:3, 78-79 | tra-prototype/README.md:3 says 'A Phase 0-5 reference implementation of TRA v1.0'. Line 78-79 says 'Phase 6 (exception hardening, human-in-the-loop, structlog, L4 evidence tracing) is pending.' Reality: Phase 6 IS implemented — 6.1 (recovery.py), 6.2 (hitl.py + --interactive), 6.3 (reporting.py, Mermaid, audit summary), 6.4 (kernel.py:293-312 _export_forensics, L4 trace), 6.5 (kernel.py:75-90 _sanitize_input + isa.py:316-330 graceful degradation). Only 6.3.1 structlog is genuinely pending. CLAUDE.md:15 and status.md:35 corroborate that Phase 6 landed in commit 4d97aa1. | Update tra-prototype/README.md:3 to 'Phase 0-6 reference implementation'. Update L78-79 to reflect that only structlog (6.3.1) is pending. The prototype README is the file a new contributor reads first — accuracy here is load-bearing.
TRA-022 | WARNING | C | Doc Consistency / Stale Docstring | tra_cli.py docstring says 'Phase 0.1.5 skeleton' with 3 subcommands — file has 4 | tra_cli.py:1-7 | tra_cli.py:1-7 docstring: 'Phase 0.1.5 skeleton ... subcommands: translate, cache-clear, audit.' The file actually implements 4 subcommands (validate at L197) and is no longer a skeleton. Stale docstrings mislead contributors and AI agents reading the file. | Update tra_cli.py:1-7 to list all 4 subcommands (translate, validate, audit, cache-clear) and drop the 'Phase 0.1.5 skeleton' label.
TRA-023 | WARNING | C | Doc Consistency / Setup Instructions | SKILL.md install instructions omit dev deps — contributor cannot run quality gates | SKILL.md:67-68 | SKILL.md:67-68 says `pip install -e .` (no [dev] extra). Section 7 'Quality gates' (SKILL.md:172-176) requires ruff, mypy, pytest — all dev deps. A new contributor following SKILL.md verbatim installs only runtime deps and cannot run the gates. They either abandon the gates or sudo-install tools globally. | Change SKILL.md:67 to `pip install -e .[dev]` (or `pip install -e '.[dev]'` for zsh). Add a note that the dev extra is required for the quality gates in §7.
TRA-024 | WARNING | C | Doc Consistency / Implementation Plan | implementation_plan.md Phase 0 all unchecked but fully delivered; file-structure lists nonexistent tests | implementation_plan.md:14-55 (Phase 0 checkboxes); :305-347 (file structure) | Every Phase 0 item (0.1.1 through 0.4.3) is marked `[ ]` but all are implemented per the codebase. The file-structure summary (L305-347) lists test files that don't exist: test_policy.py, test_cache.py, test_evidence.py, benchmark/runner.py, benchmark/test_benchmarks.py. Actual tests: test_phase0.py, test_isa.py, test_kernel.py, test_recovery.py, test_validate.py, test_modules.py, test_benchmark.py, test_anchor.py, test_reporting.py, test_phase6_hardening.py, test_utils.py. Phase 1.3, 6.3.1, 6.5.1, 6.5.2, Phase 7 markings ARE accurate. | Either check the Phase 0 boxes (`[x]`) or add a header note 'Phase 0 was delivered before this plan was last updated; checkboxes are stale.' Update the file-structure summary to match the actual test files.
TRA-025 | WARNING | C | Doc Consistency / Repo Hygiene | No .gitignore at repo root — runtime artifacts (audit_trace.jsonl, cache/, compilation_artifacts/) committed | repo root LS; status.md:48-49 acknowledges | audit_trace.jsonl (451 lines), cache/cache.db, compilation_artifacts/{glossary,entity_table,structural_map,style_profile}.{yaml,json} exist at the REPO ROOT (outside tra-prototype/) from a prior run with cwd at the repo root. The tra-prototype/.gitignore covers them locally but the repo root has no .gitignore. status.md:48-49 acknowledges the issue but defers the fix. These artifacts pollute the spec repo and could be accidentally committed. | Add a repo-root .gitignore covering /audit_trace.jsonl, /cache/, /compilation_artifacts/. Run `git rm --cached` on any tracked artifacts. Optionally `rm -rf` the existing root-level artifacts.
TRA-026 | WARNING | C | Doc Consistency / Dead Config | config.yaml cache.expire field parsed by YAML but ignored by code | config.yaml:18; config.py:46-47; cache.py:105 | config.yaml:18 sets `cache.expire: null`. BootstrapConfig.from_yaml (config.py:46-47) reads only `cache.enabled` and `cache.directory`. TranslationCache.set (cache.py:105) hardcodes `expire=None`. The field is misleading dead config — a user who sets `cache.expire: 3600` expects TTL-based eviction and gets none. | Either wire cache.expire through to TranslationCache.set (and diskcache's expire parameter), or remove the field from config.yaml and document that the cache has no TTL by design (static facts, per implementation_plan.md §0.4.2).
TRA-027 | WARNING | C | Doc Consistency / Misleading Filename | examples/expected_outputs/security_advisory_zh.L3.md is just translated markdown, not an L3 bundle | examples/expected_outputs/security_advisory_zh.L3.md (file content) | The filename implies an L3 certification bundle (target + audit trace + glossary + conformance verdict). The file contains only the translated markdown. A reader expecting the full L3 evidence package will be confused. The audit trace, glossary, entity table, and conformance summary are not present. | Rename to security_advisory_zh.L3.target.md (clarifying it's just the target text). Optionally populate a sibling security_advisory_zh.L3.bundle/ directory with the audit trace + artifacts + conformance verdict, OR add a README explaining the bundle structure.
TRA-028 | BLOCKING | D | Test Suite / Invariant Coverage | Zero test coverage on repair_segment's 'raise on new BLOCKING' clause | isa.py:515-519; test_isa.py (no such test); test_kernel.py (no such test) | Mutation testing: removing the `if new_blocking and attempt >= max_retries: raise Unrecoverable(...)` block entirely leaves all 103 tests green. Flipping `>=` to `>` (off-by-one) leaves all 103 tests green. Calling repair_segment directly with attempt=1 and new BLOCKING has no test asserting the raise behavior. The most dangerous gap: the test suite cannot detect regressions in the surgical-repair invariant's partial enforcement. | Add test_repair_segment_raises_on_new_blocking: call repair_segment with a diagnostic it cannot fix (e.g., subsystem='entity', entity absent from source) at attempt=max_retries, assert Unrecoverable raised. Also add test_repair_segment_returns_silently_at_attempt_1 documenting the current (buggy) behavior, marked xfail, to be flipped when TRA-003 is fixed.
TRA-029 | BLOCKING | D | Test Suite / Invariant Coverage | Invariant 3 (verify_output never self-scores) untested at enforcement boundary | test_phase0.py:68-82 (comment-only assertion) | Mutation testing: adding `if e.confidence_note and e.confidence_note < 0.5: diagnostics.append(...)` to verify_output leaves all 103 tests green. The existing test (test_phase0.py:68-82) adds a low-confidence record to the registry but never calls verify_output or repair_segment with that record present. It only asserts the record was added, not that it was ignored. The 'never self-score' invariant is documented but untested at the enforcement boundary. | Add test_verify_output_ignores_confidence_note: populate ctx with an EvidenceRegistry containing a low-confidence record, run verify_output on a clean target, assert zero diagnostics. Repeat for repair_segment.
TRA-030 | BLOCKING | D | Test Suite / Severity Classification | No test asserts terminology=WARNING and structural=BLOCKING severity classification | isa.py:429 (terminology=WARNING), :401-409 (structural=BLOCKING); test_isa.py | Mutation testing: changing Severity.WARNING to Severity.BLOCKING for terminology violations (isa.py:429) leaves all 103 tests green. Changing Severity.BLOCKING to Severity.WARNING for structural violations (isa.py:403) leaves all 103 tests green. The severity-classification contract is unprotected. A mutation escalating terminology to BLOCKING would silently make the L3 gate stricter than the spec intends; a mutation demoting structural to WARNING would silently make the L3 gate more permissive. | Add test_verify_output_terminology_is_warning_not_blocking and test_verify_output_structural_mismatch_is_blocking. Each should construct a minimal source/target pair, run verify_output, and assert exactly one diagnostic with the expected severity and subsystem.
TRA-031 | WARNING | D | Test Suite / Benchmark Coverage | Only 13 of 24 spec benchmark cases implemented (54%) | tests/benchmark/cases/sft.jsonl (13 cases); TRA-BENCHMARK-SUITE.md (24+ cases) | TRA-BENCHMARK-SUITE.md defines S-01..S-06, F-01..F-05, T-01..T-05, D-01..D-04, E-01..E-03 (24 cases). The prototype implements 13 (S-05, F-01..F-05, T-01..T-05, D-04, E-02) plus R-01 (regression, not in spec). Missing: S-01 (nested lists), S-02 (complex tables), S-03 (inline code vs prose — exposes the whole-doc translation gap), S-04 (blockquotes in lists), S-06 (anchors — unit-tested but not in benchmark), D-01/D-02/D-03 (domain cases), E-01 (intentional ambiguity), E-03 (broken source markdown — exposes the exception-recovery gap). Spec target is '100+'. | Add the 11 missing JSONL cases. Mark S-03 and E-03 as xfail with referenced open issues (TRA-001 and TRA-004 respectively). Document the 13/24 coverage in CLAUDE.md Known gaps.
TRA-032 | WARNING | D | Test Suite / HITL Coverage | HITL only tested for 'accept' path; 'override' and 'skip' untested; interactive=True kernel untested | test_phase6_hardening.py (only accept tested); kernel.py:214-231 (interactive branch) | test_phase6_hardening.py tests HITL review_decision with the 'accept' resolution only. The 'override' and 'skip' resolutions have no test. The kernel's interactive=True branch (kernel.py:214-231) is never exercised in tests. A mutation breaking the override or skip path would go undetected. | Parametrize test_hitl_review_decision over ['accept', 'override', 'skip']. Add test_kernel_interactive_mode: construct TRAKernel(config, interactive=True), force an UNRECOVERABLE repair, mock stdin to provide each resolution, assert the target is updated correctly.
TRA-033 | WARNING | D | Test Suite / LLM Seam | LLM seam degradation tested for RuntimeError only; other exception types untested | test_phase6_hardening.py:test_graceful_degradation_on_llm_failure | The graceful-degradation test supplies an llm_translate that raises RuntimeError. The catch at isa.py:316 is `except Exception` which covers all exception types, but only RuntimeError is tested. A mutation narrowing the catch to `except RuntimeError` would leave 102 of 103 tests green. Empty-string returns and None returns from llm_translate are also untested. | Parametrize the test over [RuntimeError, ValueError, TypeError, OSError, KeyboardInterrupt]. Add tests for llm_translate returning '' and None.
TRA-034 | INFO | D | Test Suite / Quality | conftest.py fixtures used only by test_phase0.py — 10 other test files ignore it | tests/conftest.py; grep for fixture usage | conftest.py defines 6 fixtures (sample_glossary, sample_entities, cache_context, evidence_registry, sample_evidence, config). Only test_phase0.py imports them. The other 10 test files build fixtures inline, leading to duplication. Not a correctness issue but a maintainability one — fixture changes don't propagate. | Refactor test_isa.py, test_kernel.py, test_validate.py, test_benchmark.py to use the shared fixtures. Add new fixtures for common patterns (e.g., a minimal source markdown, a fully-built RuntimeContext).
TRA-035 | INFO | D | Test Suite / Mutation Coverage | Invariant mutation catch rate: 5 of 12 scenarios (42%) | Track D mutation testing (4 invariants × 3 mutations) | Across the 4 critical invariants, 12 mutation scenarios were tested. 5 caught (42%): all 3 mutations on Invariant 1 (canonical terminology), 2 of 3 on Invariant 2 (entity immutability at construction). 7 missed: 1 on Invariant 2 (post-construction mutation), 3 on Invariant 3 (confidence_note reads in verify/repair/loop), 3 on Invariant 4 (repair-segment raise behavior). The test suite protects the data-model invariants well but the behavioral invariants poorly. | Close the 3 BLOCKING gaps (TRA-028, TRA-029, TRA-030) to bring the catch rate from 42% to 100% on the critical invariants. Consider adding a CI mutation-testing step (mutmut or cosmic-ray) to prevent future regressions.

## Track A - Spec Conformance
ID | Severity | Category | Title | Evidence | Detail | Suggested Fix
TRA-001 | BLOCKING | Spec Conformance / ISA Contract | TRANSLATE_SEGMENT receives whole document, not a segment | kernel.py:186; TRA-ISA-REFERENCE.md:48-49; cache.py:12-13 | The ISA contract (TRA-ISA-REFERENCE.md §TRANSLATE_SEGMENT) mandates that the instruction operates on 'a specific source segment (sentence, list item, or table cell)'. The kernel passes the entire source markdown as one segment (kernel.py:186 `translate_segment(src, ...)`). Consequences: cache keys are per-document (violating cache.py:12-13 'never a whole document'), RepairAttempt.segment_index is always 0, L4 line-by-line trace uses substring heuristic rather than structural mapping, and is_no_translate_zone markers on code blocks are never consulted (S-03 violated). The kernel.py:184 inline comment admits 'Segment granularity is wired in Phase 3' — Phase 3 never landed. | Refactor _execute_translation to iterate StructuralMap leaf nodes (paragraphs, list items, table cells, headings), call translate_segment per leaf, and reassemble via the structural map. Skip nodes where is_no_translate_zone=True.
TRA-002 | BLOCKING | Spec Conformance / Module Extension | Module registry is the sanctioned extension point but kernel bypasses it | kernel.py:43,106; isa.py:50,54; CLAUDE.md:40; SKILL.md:151-163 | CLAUDE.md and SKILL.md §6 document the module registry as the 'only sanctioned path' for new language bridges: `registry = build_default_registry(); registry.register(my_module.as_interface())`. In production code, the kernel hard-codes `ZHENModule()` directly (kernel.py:43 import, kernel.py:106 instantiation; isa.py:50,54 same pattern). Grep confirms ZERO production callers of build_default_registry or registry_for_language_pair. A user following SKILL.md §6 verbatim will find their registered module is NOT used by `tra_cli.py translate`. | Replace the hard-coded `ZHENModule()` in kernel.py and isa.py with a registry lookup: `module = registry_for_language_pair(config.language_pair)`. Inject the module via constructor instead of module-level singleton.
TRA-003 | BLOCKING | Spec Conformance / Critical Invariant | repair_segment does not enforce surgical invariant at function boundary | isa.py:515-519; TRA-ISA-REFERENCE.md:79; TRA-SPECIFICATION.md:83 | The spec mandates 'Repair must resolve the specific violation without introducing new ones' (TRA-ISA-REFERENCE.md:79, mirrored in TRA-SPECIFICATION.md:83, CLAUDE.md:79, AGENTS.md:33, README.md:123). The code (isa.py:515-519) only raises Unrecoverable when `new_blocking and attempt >= max_retries`. At attempt=1 with max_retries=3, a repair that introduces new BLOCKING returns silently with resolved=False. Empirically confirmed: calling repair_segment(target='成立 Valid', attempt=1, max_retries=3) returns 'Confirmed Valid' (containing the forbidden drift target 'Valid') without raising. The kernel's _repair_loop catches this by re-queuing, but a direct caller receives broken output with no exception. | Remove the `attempt >= max_retries` guard from the new-BLOCKING check. Raise Unrecoverable unconditionally on any new BLOCKING, regardless of attempt number. Add a regression test that calls repair_segment directly with attempt=1 and asserts the raise.
TRA-004 | BLOCKING | Spec Conformance / Exception Recovery | 4 of 5 TRA-EXCEPTION recovery procedures are unreachable | isa.py:84 (BrokenMarkdown raised, kernel.py:129 not caught); recovery.py:154 | Spec §6 mandates deterministic recovery for all 5 TRA-EXCEPTION types. Grep across tra/ for `raise UnknownTerm¦raise CertaintyConflict¦raise EntityAmbiguity` returns ZERO hits — these exception classes exist but are never raised in production code paths. BrokenMarkdown IS raised by analyze_document (isa.py:84) but kernel.py:129 calls analyze_document with NO try/except, so a malformed source crashes the kernel with no EXCEPTION_HANDLER invocation. Only GlossaryConflict (build_glossary) and Unrecoverable (repair_segment) reach route_exception. The recovery.py dispatcher and 3 of its 5 handlers are dead code. | Wrap each ISA call in kernel.run() with try/except TRAException and route through self._recover(). Add UNKNOWN_TERM / CERTAINTY_CONFLICT / ENTITY_AMBIGUITY raise sites in the relevant ISA instructions (translate_segment for UNKNOWN_TERM, verify_output for CERTAINTY_CONFLICT, build_entity_table for ENTITY_AMBIGUITY).
TRA-005 | BLOCKING | Spec Conformance / L3 Gate | kernel.run() does not enforce the L3 zero-BLOCKING gate | kernel.py:157; tra_cli.py:106-120; TRA-CONFORMANCE-GUIDE.md:51 | Per TRA-CONFORMANCE-GUIDE.md:51, 'If [BLOCKING diagnostics are] present, certification is denied.' The kernel's run() method (kernel.py:157) returns the target unconditionally, even when _repair_loop exhausts max_retries with BLOCKING diagnostics still present. The CLI (tra_cli.py:106-120) only prints a warning. Only validate.py and benchmark.py enforce zero-BLOCKING. A user running `tra_cli.py translate --level L3` on a document that produces BLOCKING diagnostics receives a 'translated' output and no error signal. | After _repair_loop, re-run verify_output. If any BLOCKING remains, raise a TRAException (e.g., ConformanceFailure) that the CLI catches and exits 1 with a clear message. Document that `translate` is a best-effort runner and `validate` is the certification gate.
TRA-006 | WARNING | Spec Conformance / Policy Engine | PolicyResolver is scaffolding — never invoked in production | policy.py:13 (definition); test_phase0.py:23 (only test import) | The 6-priority PolicyResolver exists but is never called by the kernel or ISA. Grep confirms only the definition and a test import. The policy_stack is consulted only for cache-key hashing (cache.py:65), never for arbitration. verify_output has no Factual-Integrity check (strings like '<60ms', '96-core', '<5MB' aren't entities and aren't verified), no structural check beyond heading count, no fluency check. The spec's scope rules (code blocks: only Fluency relaxable; headings: Factual beats Structural) are not implemented. | Wire PolicyResolver into verify_output and repair_segment. At minimum, implement the Factual Integrity check (numbers/units/versions preservation beyond entity extraction) and the scope rules for code blocks vs headings.
TRA-007 | WARNING | Spec Conformance / Kernel Transitions | Kernel transitions fire BEFORE ISA completion, not after | kernel.py:127-157; CLAUDE.md:19; TRA-SPECIFICATION.md §2.1 | CLAUDE.md:19 claims 'transitions only on successful ISA completion'. The kernel calls `self._transition(KernelState.ANALYZE_DOCUMENT)` at kernel.py:128 BEFORE calling `analyze_document(...)` at kernel.py:129. If the ISA raises, the state has already advanced. The spec §2.1 state diagram includes an EXCEPTION_HANDLER state for failed ISA calls — the kernel does not model this state at all. | Move each `self._transition(...)` call to AFTER the corresponding ISA call returns successfully. Add a KernelState.EXCEPTION_HANDLER state (or route via _recover) for the failure path. Update CLAUDE.md:19 to match the implementation if you choose not to fix the code.
TRA-008 | WARNING | Spec Conformance / Structural Integrity | Anchor rewrite_links defined but never called — S-06 dead in production | anchor.py:rewrite_links; kernel.py:142-156 (no rewrite call) | AnchorRegistry.rewrite_links is implemented and unit-tested (test_anchor.py S-06 case), but the kernel's _execute_translation never calls it. Translated headings produce new slugs that don't match internal `#anchor` links in the rest of the document. The structural integrity check in verify_output only counts headings — it does not verify link integrity. | After reassembling translated segments, call `registry.rewrite_links(translated_ast)` before returning the target. Add a verify_output check that every internal `#link` resolves to a heading slug in the target.
TRA-009 | WARNING | Spec Conformance / Terminological Consistency | Terminology violations classified as WARNING, not BLOCKING | isa.py:429 | When a source glossary term leaks into the target untranslated, verify_output (isa.py:429) emits a WARNING. Per Spec §5, Terminological Consistency is Priority 4 — higher than Fluency (6) but lower than Entity (3). The spec does not mandate BLOCKING for terminology drift, but the L3 gate's 'zero BLOCKING' criterion means terminology drift alone never blocks certification. This may be intentional but should be documented. | Either escalate terminology violations to BLOCKING at L3+ (stricter than spec, but safer), or document the WARNING classification explicitly in CLAUDE.md and TRA-CONFORMANCE-GUIDE.md.
TRA-010 | WARNING | Spec Conformance / Memory Model | Memory model immutability claims unenforced | memory.py:172 (RuntimeContext not frozen); config.py:23 (BootstrapConfig not frozen) | Spec §4 describes Immutable Config (read-only) and Audit Memory (append-only). In code, BootstrapConfig is a plain Pydantic BaseModel (not frozen=True). The CLI directly mutates it (tra_cli.py:87-89 sets level/lang on the config object). AuditTrail is append-only by API convention but nothing prevents a stray `.records.clear()` call. count_blocking is a stub returning 0 (see TRA-016). | Add `model_config = ConfigDict(frozen=True)` to BootstrapConfig. Make AuditTrail.records a tuple or use a frozen list wrapper. Implement or remove count_blocking.

## Track B - Code Quality
ID | Severity | Category | Title | Evidence | Detail | Suggested Fix
TRA-011 | BLOCKING | Code Quality / Cache Invalidation | cache-clear --pattern is a silent no-op (diskcache.delete takes literal key) | cache.py:107-115; tra_cli.py:123-132 | TranslationCache.invalidate(pattern) calls `self._cache.delete(pattern)`. diskcache's delete() takes a LITERAL key, not a glob. Empirically confirmed: invalidate('test*') on a cache with 3 entries deletes 0 (3→3); the literal-key invalidate works (3→2). The CLI (tra_cli.py:130) then prints 'Cache invalidated: <pattern>' unconditionally — lying to the user. A user who runs `tra cache-clear --pattern 'translation:*'` to invalidate stale entries believes they were cleared; they weren't. This could serve stale translations indefinitely. | Implement glob via `for key in self._cache.iterkeys(): if fnmatch(key, pattern): self._cache.delete(key)`. Alternatively, drop --pattern and only support `cache-clear` (full clear). Update the CLI to print the actual count deleted.
TRA-012 | WARNING | Code Quality / Input Sanitization | _sanitize_input bypassed at validate and benchmark boundaries | kernel.py:75-90 (regex); validate.py:71-72; benchmark.py:102-104 | The _sanitize_input regex (kernel.py:78-80) correctly strips null bytes, C0 control chars, DEL, Unicode bidi overrides (\u202a-\u202e), and BOM (\ufeff). It is only called from TRAKernel.run() (kernel.py:125). validate_translation (validate.py:71-72) calls analyze_document(source) directly with no sanitization. BenchmarkRunner.run_case (benchmark.py:102-104) re-verifies via analyze_document(case.source) unsanitized. A malicious candidate file with bidi-override characters could be processed by `tra validate` without sanitization, potentially confusing auditors who inspect the rendered output. | Move _sanitize_input to a shared utility (e.g., utils.py or a new security.py). Call it at the top of validate_translation, analyze_document, and the benchmark re-verify block. Add a test that confirms bidi-override characters are stripped at every entry point.
TRA-013 | WARNING | Code Quality / Reproducibility | Audit trail is NOT byte-reproducible (uuid4 + datetime.now) | diagnostics.py:40 (uuid4); diagnostics.py:58 (datetime.now(UTC)) | Empirically confirmed: two runs of identical source produce identical target text, identical cache.db, identical glossary/entity/smap/style/exec_log/repair_history — but DIFFERENT audit_trace.jsonl. Diff shows every record differs in `timestamp`, and records 1-3 also differ in all evidence_chain IDs (random ev_<uuid4.hex[:12]>). For L4 forensic audits (legal/security per TRA-CONFORMANCE-GUIDE.md), this means you cannot cryptographically prove 'this audit trail corresponds to this output' by hashing the trail. The R-01 regression test (test_benchmark.py:65-71) only checks output equality, not audit-trail equality. | Make evidence IDs deterministic: `ev_{sha256(content)[:12]}` instead of uuid4. Replace datetime.now(UTC) with a deterministic timestamp derived from the source hash, or accept an optional `timestamp` parameter. Add a test asserting audit-trail byte-equality across two runs of the same input.
TRA-014 | WARNING | Security / Path Traversal | No path-traversal protection on config-supplied paths | config.py:23-55; kernel.py:240-312 (mkdir + write) | BootstrapConfig.from_yaml accepts compilation_dir, audit_trace, cache_directory from config.yaml with no sanitization. A malicious config with `compilation_dir: '../../../etc'`, `audit_trace: '/tmp/evil.jsonl'`, `cache_directory: '/var/tmp/evil-cache'` is accepted and the kernel writes 6-8 files there. AuditTrail.flush() calls mkdir(parents=True) on arbitrary paths. Acceptable for a trusted-config prototype; unacceptable for production. | Resolve all config paths against a project root. Reject paths containing `..` or absolute paths outside the project root. Add a test that confirms a malicious config is rejected.
TRA-015 | WARNING | Code Quality / Audit Trail | Double audit record on LLM graceful degradation | isa.py:316-346 | When llm_translate raises, isa.py:322-330 appends a TRANSLATE_SEGMENT record with artifact_snapshot={'degraded': True, 'reason': ...}. The code then FALLS THROUGH to isa.py:334-346, appending ANOTHER TRANSLATE_SEGMENT record (with evidence_chain, no degraded flag). Empirically verified: degraded translation produces 2 records — Record 0 {'degraded': True, ...}, Record 1 {}. An L3 auditor inspecting the LAST TRANSLATE_SEGMENT per segment misses the degradation. The existing test test_graceful_degradation_on_llm_failure uses any(...) so it passes but doesn't catch the double-record issue. | Add a `return` statement after the degradation-notice audit.append, OR merge the degraded flag into the single normal-path record. Update the test to assert exactly one TRANSLATE_SEGMENT record per segment.
TRA-016 | WARNING | Code Quality / Dead Code | AuditTrail.count_blocking is a stub returning 0 unconditionally | diagnostics.py:159-166 | The method name suggests it counts BLOCKING diagnostics in the audit trail. The implementation returns 0 unconditionally with a comment 'hook for VERIFY to populate'. Zero callers in production or tests. If a future contributor trusts the method name, they will get a false L3 PASS. Real counting lives in reporting.summarize_audit and validate.ValidationReport. | Either implement count_blocking by scanning the audit trail for records with 'BLOCKING' in flags_raised, or delete the method and direct readers to reporting.summarize_audit.
TRA-017 | WARNING | Code Quality / Dependency Hygiene | 5 unused dependencies inflate install footprint (~50+ transitive packages) | pyproject.toml:10-21; grep across tra/ for imports | litellm (>=1.49), structlog (>=24.1), pydantic-settings (>=2.3), mdit-py-plugins (>=0.4), and black (>=24.4, dev) are listed but never imported. litellm alone pulls ~30 transitive deps (openai, tiktoken, tokenizers, huggingface-hub, httpx, aiohttp, jinja2, jsonschema, ...). The LLM seam is wired as a caller-supplied Callable, so litellm is not actually needed at runtime. pytest-asyncio (dev) is also unused (asyncio_mode=auto set but zero async tests). Total install: ~50+ packages, hundreds of MB, for a rule-based prototype. | Move litellm to optional-dependencies.llm. Drop pydantic-settings, mdit-py-plugins, structlog, black, pytest-asyncio from the manifest. Add a 'Dependency hygiene' bullet to CLAUDE.md Known gaps.
TRA-018 | WARNING | Code Quality / Pydantic v2 | Immutability claims on Entity and BootstrapConfig unenforced (no frozen=True) | memory.py:154 (Entity); config.py:23 (BootstrapConfig) | Entity is documented as 'an immutable identifier isolated from natural-language translation' but is a plain BaseModel with mutable=True default. BootstrapConfig is described as the 'Immutable Config (read-only)' memory segment but is also a plain BaseModel. The CLI (tra_cli.py:87-89) directly mutates BootstrapConfig. Zero ConfigDict(frozen=True) anywhere in the codebase. Zero Field constraints (min_length, pattern, ge, le) on any model. | Add `model_config = ConfigDict(frozen=True)` to Entity, GlossaryEntry, ForbiddenMapping, and BootstrapConfig. For RuntimeContext (which must be mutable), leave unfrozen but document why. Add Field constraints where applicable (e.g., ConformanceLevel enum, non-empty source strings).
TRA-019 | WARNING | Code Quality / Assert Usage | 2 runtime asserts in kernel.py stripped under python -O | kernel.py:130-131 | kernel.py:130-131 uses `assert self.ctx.document_profile is not None` and `assert self.ctx.structural_map is not None` for runtime validation. Python asserts are stripped when the interpreter runs with -O (optimized mode). A production deployment using -O would silently skip these checks. The spec's 'never skip instructions' principle suggests these should be hard raises. | Replace `assert x is not None` with `if x is None: raise TRAException(...)`. Reserve assert for invariants that are truly impossible to violate.

## Track C - Doc Consistency
ID | Severity | Category | Title | Evidence | Detail | Suggested Fix
TRA-020 | BLOCKING | Doc Consistency / Known Gaps | CLAUDE.md 'Known gaps (honest, not yet addressed)' lists only 3 of ~16 material gaps | CLAUDE.md:42-46 | CLAUDE.md:42-46 labels the list 'Known gaps (honest, not yet addressed)' but enumerates only: structlog unused, no asyncio parallelism, no cross-run glossary/entity caching. At least 16 material gaps exist (TRA-001 through TRA-019 in this audit, plus Phase 7 items). The word 'honest' is itself misleading when the list omits the most material gaps (segment-level granularity, registry bypass, repair-attempt-1, exception recovery, L3 gate not enforced in translate, count_blocking stub, cache-clear no-op, etc.). | Replace the 3-bullet list with a numbered list of all known material gaps (this audit's TRA-001 through TRA-019 is a starting point). Drop the word 'honest' or make it true. Cross-reference each gap to its finding ID for traceability.
TRA-021 | BLOCKING | Doc Consistency / Status Header | tra-prototype/README.md says 'Phase 0-5' and 'Phase 6 pending' — both false | tra-prototype/README.md:3, 78-79 | tra-prototype/README.md:3 says 'A Phase 0-5 reference implementation of TRA v1.0'. Line 78-79 says 'Phase 6 (exception hardening, human-in-the-loop, structlog, L4 evidence tracing) is pending.' Reality: Phase 6 IS implemented — 6.1 (recovery.py), 6.2 (hitl.py + --interactive), 6.3 (reporting.py, Mermaid, audit summary), 6.4 (kernel.py:293-312 _export_forensics, L4 trace), 6.5 (kernel.py:75-90 _sanitize_input + isa.py:316-330 graceful degradation). Only 6.3.1 structlog is genuinely pending. CLAUDE.md:15 and status.md:35 corroborate that Phase 6 landed in commit 4d97aa1. | Update tra-prototype/README.md:3 to 'Phase 0-6 reference implementation'. Update L78-79 to reflect that only structlog (6.3.1) is pending. The prototype README is the file a new contributor reads first — accuracy here is load-bearing.
TRA-022 | WARNING | Doc Consistency / Stale Docstring | tra_cli.py docstring says 'Phase 0.1.5 skeleton' with 3 subcommands — file has 4 | tra_cli.py:1-7 | tra_cli.py:1-7 docstring: 'Phase 0.1.5 skeleton ... subcommands: translate, cache-clear, audit.' The file actually implements 4 subcommands (validate at L197) and is no longer a skeleton. Stale docstrings mislead contributors and AI agents reading the file. | Update tra_cli.py:1-7 to list all 4 subcommands (translate, validate, audit, cache-clear) and drop the 'Phase 0.1.5 skeleton' label.
TRA-023 | WARNING | Doc Consistency / Setup Instructions | SKILL.md install instructions omit dev deps — contributor cannot run quality gates | SKILL.md:67-68 | SKILL.md:67-68 says `pip install -e .` (no [dev] extra). Section 7 'Quality gates' (SKILL.md:172-176) requires ruff, mypy, pytest — all dev deps. A new contributor following SKILL.md verbatim installs only runtime deps and cannot run the gates. They either abandon the gates or sudo-install tools globally. | Change SKILL.md:67 to `pip install -e .[dev]` (or `pip install -e '.[dev]'` for zsh). Add a note that the dev extra is required for the quality gates in §7.
TRA-024 | WARNING | Doc Consistency / Implementation Plan | implementation_plan.md Phase 0 all unchecked but fully delivered; file-structure lists nonexistent tests | implementation_plan.md:14-55 (Phase 0 checkboxes); :305-347 (file structure) | Every Phase 0 item (0.1.1 through 0.4.3) is marked `[ ]` but all are implemented per the codebase. The file-structure summary (L305-347) lists test files that don't exist: test_policy.py, test_cache.py, test_evidence.py, benchmark/runner.py, benchmark/test_benchmarks.py. Actual tests: test_phase0.py, test_isa.py, test_kernel.py, test_recovery.py, test_validate.py, test_modules.py, test_benchmark.py, test_anchor.py, test_reporting.py, test_phase6_hardening.py, test_utils.py. Phase 1.3, 6.3.1, 6.5.1, 6.5.2, Phase 7 markings ARE accurate. | Either check the Phase 0 boxes (`[x]`) or add a header note 'Phase 0 was delivered before this plan was last updated; checkboxes are stale.' Update the file-structure summary to match the actual test files.
TRA-025 | WARNING | Doc Consistency / Repo Hygiene | No .gitignore at repo root — runtime artifacts (audit_trace.jsonl, cache/, compilation_artifacts/) committed | repo root LS; status.md:48-49 acknowledges | audit_trace.jsonl (451 lines), cache/cache.db, compilation_artifacts/{glossary,entity_table,structural_map,style_profile}.{yaml,json} exist at the REPO ROOT (outside tra-prototype/) from a prior run with cwd at the repo root. The tra-prototype/.gitignore covers them locally but the repo root has no .gitignore. status.md:48-49 acknowledges the issue but defers the fix. These artifacts pollute the spec repo and could be accidentally committed. | Add a repo-root .gitignore covering /audit_trace.jsonl, /cache/, /compilation_artifacts/. Run `git rm --cached` on any tracked artifacts. Optionally `rm -rf` the existing root-level artifacts.
TRA-026 | WARNING | Doc Consistency / Dead Config | config.yaml cache.expire field parsed by YAML but ignored by code | config.yaml:18; config.py:46-47; cache.py:105 | config.yaml:18 sets `cache.expire: null`. BootstrapConfig.from_yaml (config.py:46-47) reads only `cache.enabled` and `cache.directory`. TranslationCache.set (cache.py:105) hardcodes `expire=None`. The field is misleading dead config — a user who sets `cache.expire: 3600` expects TTL-based eviction and gets none. | Either wire cache.expire through to TranslationCache.set (and diskcache's expire parameter), or remove the field from config.yaml and document that the cache has no TTL by design (static facts, per implementation_plan.md §0.4.2).
TRA-027 | WARNING | Doc Consistency / Misleading Filename | examples/expected_outputs/security_advisory_zh.L3.md is just translated markdown, not an L3 bundle | examples/expected_outputs/security_advisory_zh.L3.md (file content) | The filename implies an L3 certification bundle (target + audit trace + glossary + conformance verdict). The file contains only the translated markdown. A reader expecting the full L3 evidence package will be confused. The audit trace, glossary, entity table, and conformance summary are not present. | Rename to security_advisory_zh.L3.target.md (clarifying it's just the target text). Optionally populate a sibling security_advisory_zh.L3.bundle/ directory with the audit trace + artifacts + conformance verdict, OR add a README explaining the bundle structure.

## Track D - Test Suite
ID | Severity | Category | Title | Evidence | Detail | Suggested Fix
TRA-028 | BLOCKING | Test Suite / Invariant Coverage | Zero test coverage on repair_segment's 'raise on new BLOCKING' clause | isa.py:515-519; test_isa.py (no such test); test_kernel.py (no such test) | Mutation testing: removing the `if new_blocking and attempt >= max_retries: raise Unrecoverable(...)` block entirely leaves all 103 tests green. Flipping `>=` to `>` (off-by-one) leaves all 103 tests green. Calling repair_segment directly with attempt=1 and new BLOCKING has no test asserting the raise behavior. The most dangerous gap: the test suite cannot detect regressions in the surgical-repair invariant's partial enforcement. | Add test_repair_segment_raises_on_new_blocking: call repair_segment with a diagnostic it cannot fix (e.g., subsystem='entity', entity absent from source) at attempt=max_retries, assert Unrecoverable raised. Also add test_repair_segment_returns_silently_at_attempt_1 documenting the current (buggy) behavior, marked xfail, to be flipped when TRA-003 is fixed.
TRA-029 | BLOCKING | Test Suite / Invariant Coverage | Invariant 3 (verify_output never self-scores) untested at enforcement boundary | test_phase0.py:68-82 (comment-only assertion) | Mutation testing: adding `if e.confidence_note and e.confidence_note < 0.5: diagnostics.append(...)` to verify_output leaves all 103 tests green. The existing test (test_phase0.py:68-82) adds a low-confidence record to the registry but never calls verify_output or repair_segment with that record present. It only asserts the record was added, not that it was ignored. The 'never self-score' invariant is documented but untested at the enforcement boundary. | Add test_verify_output_ignores_confidence_note: populate ctx with an EvidenceRegistry containing a low-confidence record, run verify_output on a clean target, assert zero diagnostics. Repeat for repair_segment.
TRA-030 | BLOCKING | Test Suite / Severity Classification | No test asserts terminology=WARNING and structural=BLOCKING severity classification | isa.py:429 (terminology=WARNING), :401-409 (structural=BLOCKING); test_isa.py | Mutation testing: changing Severity.WARNING to Severity.BLOCKING for terminology violations (isa.py:429) leaves all 103 tests green. Changing Severity.BLOCKING to Severity.WARNING for structural violations (isa.py:403) leaves all 103 tests green. The severity-classification contract is unprotected. A mutation escalating terminology to BLOCKING would silently make the L3 gate stricter than the spec intends; a mutation demoting structural to WARNING would silently make the L3 gate more permissive. | Add test_verify_output_terminology_is_warning_not_blocking and test_verify_output_structural_mismatch_is_blocking. Each should construct a minimal source/target pair, run verify_output, and assert exactly one diagnostic with the expected severity and subsystem.
TRA-031 | WARNING | Test Suite / Benchmark Coverage | Only 13 of 24 spec benchmark cases implemented (54%) | tests/benchmark/cases/sft.jsonl (13 cases); TRA-BENCHMARK-SUITE.md (24+ cases) | TRA-BENCHMARK-SUITE.md defines S-01..S-06, F-01..F-05, T-01..T-05, D-01..D-04, E-01..E-03 (24 cases). The prototype implements 13 (S-05, F-01..F-05, T-01..T-05, D-04, E-02) plus R-01 (regression, not in spec). Missing: S-01 (nested lists), S-02 (complex tables), S-03 (inline code vs prose — exposes the whole-doc translation gap), S-04 (blockquotes in lists), S-06 (anchors — unit-tested but not in benchmark), D-01/D-02/D-03 (domain cases), E-01 (intentional ambiguity), E-03 (broken source markdown — exposes the exception-recovery gap). Spec target is '100+'. | Add the 11 missing JSONL cases. Mark S-03 and E-03 as xfail with referenced open issues (TRA-001 and TRA-004 respectively). Document the 13/24 coverage in CLAUDE.md Known gaps.
TRA-032 | WARNING | Test Suite / HITL Coverage | HITL only tested for 'accept' path; 'override' and 'skip' untested; interactive=True kernel untested | test_phase6_hardening.py (only accept tested); kernel.py:214-231 (interactive branch) | test_phase6_hardening.py tests HITL review_decision with the 'accept' resolution only. The 'override' and 'skip' resolutions have no test. The kernel's interactive=True branch (kernel.py:214-231) is never exercised in tests. A mutation breaking the override or skip path would go undetected. | Parametrize test_hitl_review_decision over ['accept', 'override', 'skip']. Add test_kernel_interactive_mode: construct TRAKernel(config, interactive=True), force an UNRECOVERABLE repair, mock stdin to provide each resolution, assert the target is updated correctly.
TRA-033 | WARNING | Test Suite / LLM Seam | LLM seam degradation tested for RuntimeError only; other exception types untested | test_phase6_hardening.py:test_graceful_degradation_on_llm_failure | The graceful-degradation test supplies an llm_translate that raises RuntimeError. The catch at isa.py:316 is `except Exception` which covers all exception types, but only RuntimeError is tested. A mutation narrowing the catch to `except RuntimeError` would leave 102 of 103 tests green. Empty-string returns and None returns from llm_translate are also untested. | Parametrize the test over [RuntimeError, ValueError, TypeError, OSError, KeyboardInterrupt]. Add tests for llm_translate returning '' and None.
TRA-034 | INFO | Test Suite / Quality | conftest.py fixtures used only by test_phase0.py — 10 other test files ignore it | tests/conftest.py; grep for fixture usage | conftest.py defines 6 fixtures (sample_glossary, sample_entities, cache_context, evidence_registry, sample_evidence, config). Only test_phase0.py imports them. The other 10 test files build fixtures inline, leading to duplication. Not a correctness issue but a maintainability one — fixture changes don't propagate. | Refactor test_isa.py, test_kernel.py, test_validate.py, test_benchmark.py to use the shared fixtures. Add new fixtures for common patterns (e.g., a minimal source markdown, a fully-built RuntimeContext).
TRA-035 | INFO | Test Suite / Mutation Coverage | Invariant mutation catch rate: 5 of 12 scenarios (42%) | Track D mutation testing (4 invariants × 3 mutations) | Across the 4 critical invariants, 12 mutation scenarios were tested. 5 caught (42%): all 3 mutations on Invariant 1 (canonical terminology), 2 of 3 on Invariant 2 (entity immutability at construction). 7 missed: 1 on Invariant 2 (post-construction mutation), 3 on Invariant 3 (confidence_note reads in verify/repair/loop), 3 on Invariant 4 (repair-segment raise behavior). The test suite protects the data-model invariants well but the behavioral invariants poorly. | Close the 3 BLOCKING gaps (TRA-028, TRA-029, TRA-030) to bring the catch rate from 42% to 100% on the critical invariants. Consider adding a CI mutation-testing step (mutmut or cosmic-ray) to prevent future regressions.

## Remediation Backlog
Priority | ID | Severity | Category | Title | Suggested Fix | Estimated Effort
P1 | TRA-001 | BLOCKING | Spec Conformance / ISA Contract | TRANSLATE_SEGMENT receives whole document, not a segment | Refactor _execute_translation to iterate StructuralMap leaf nodes (paragraphs, list items, table cells, headings), call translate_segment per leaf, and reassemble via the structural map. Skip nodes where is_no_translate_zone=True. | Large (1-2 days)
P2 | TRA-002 | BLOCKING | Spec Conformance / Module Extension | Module registry is the sanctioned extension point but kernel bypasses it | Replace the hard-coded `ZHENModule()` in kernel.py and isa.py with a registry lookup: `module = registry_for_language_pair(config.language_pair)`. Inject the module via constructor instead of module-level singleton. | Medium (4-6h)
P3 | TRA-003 | BLOCKING | Spec Conformance / Critical Invariant | repair_segment does not enforce surgical invariant at function boundary | Remove the `attempt >= max_retries` guard from the new-BLOCKING check. Raise Unrecoverable unconditionally on any new BLOCKING, regardless of attempt number. Add a regression test that calls repair_segment directly with attempt=1 and asserts the raise. | Small (1-2h)
P4 | TRA-004 | BLOCKING | Spec Conformance / Exception Recovery | 4 of 5 TRA-EXCEPTION recovery procedures are unreachable | Wrap each ISA call in kernel.run() with try/except TRAException and route through self._recover(). Add UNKNOWN_TERM / CERTAINTY_CONFLICT / ENTITY_AMBIGUITY raise sites in the relevant ISA instructions (translate_segment for UNKNOWN_TERM, verify_output for CERTAINTY_CONFLICT, build_entity_table for ENTITY_AMBIGUITY). | Medium (4-6h)
P5 | TRA-005 | BLOCKING | Spec Conformance / L3 Gate | kernel.run() does not enforce the L3 zero-BLOCKING gate | After _repair_loop, re-run verify_output. If any BLOCKING remains, raise a TRAException (e.g., ConformanceFailure) that the CLI catches and exits 1 with a clear message. Document that `translate` is a best-effort runner and `validate` is the certification gate. | Small (2-3h)
P6 | TRA-011 | BLOCKING | Code Quality / Cache Invalidation | cache-clear --pattern is a silent no-op (diskcache.delete takes literal key) | Implement glob via `for key in self._cache.iterkeys(): if fnmatch(key, pattern): self._cache.delete(key)`. Alternatively, drop --pattern and only support `cache-clear` (full clear). Update the CLI to print the actual count deleted. | Small (1-2h)
P7 | TRA-020 | BLOCKING | Doc Consistency / Known Gaps | CLAUDE.md 'Known gaps (honest, not yet addressed)' lists only 3 of ~16 material gaps | Replace the 3-bullet list with a numbered list of all known material gaps (this audit's TRA-001 through TRA-019 is a starting point). Drop the word 'honest' or make it true. Cross-reference each gap to its finding ID for traceability. | Small (1h, doc only)
P8 | TRA-021 | BLOCKING | Doc Consistency / Status Header | tra-prototype/README.md says 'Phase 0-5' and 'Phase 6 pending' — both false | Update tra-prototype/README.md:3 to 'Phase 0-6 reference implementation'. Update L78-79 to reflect that only structlog (6.3.1) is pending. The prototype README is the file a new contributor reads first — accuracy here is load-bearing. | Small (30min, doc only)
P9 | TRA-028 | BLOCKING | Test Suite / Invariant Coverage | Zero test coverage on repair_segment's 'raise on new BLOCKING' clause | Add test_repair_segment_raises_on_new_blocking: call repair_segment with a diagnostic it cannot fix (e.g., subsystem='entity', entity absent from source) at attempt=max_retries, assert Unrecoverable raised. Also add test_repair_segment_returns_silently_at_attempt_1 documenting the current (buggy) behavior, marked xfail, to be flipped when TRA-003 is fixed. | Small (1-2h)
P10 | TRA-029 | BLOCKING | Test Suite / Invariant Coverage | Invariant 3 (verify_output never self-scores) untested at enforcement boundary | Add test_verify_output_ignores_confidence_note: populate ctx with an EvidenceRegistry containing a low-confidence record, run verify_output on a clean target, assert zero diagnostics. Repeat for repair_segment. | Small (1h)
P11 | TRA-030 | BLOCKING | Test Suite / Severity Classification | No test asserts terminology=WARNING and structural=BLOCKING severity classification | Add test_verify_output_terminology_is_warning_not_blocking and test_verify_output_structural_mismatch_is_blocking. Each should construct a minimal source/target pair, run verify_output, and assert exactly one diagnostic with the expected severity and subsystem. | Small (1h)
P12 | TRA-006 | WARNING | Spec Conformance / Policy Engine | PolicyResolver is scaffolding — never invoked in production | Wire PolicyResolver into verify_output and repair_segment. At minimum, implement the Factual Integrity check (numbers/units/versions preservation beyond entity extraction) and the scope rules for code blocks vs headings. | Large (1-2 days)
P13 | TRA-007 | WARNING | Spec Conformance / Kernel Transitions | Kernel transitions fire BEFORE ISA completion, not after | Move each `self._transition(...)` call to AFTER the corresponding ISA call returns successfully. Add a KernelState.EXCEPTION_HANDLER state (or route via _recover) for the failure path. Update CLAUDE.md:19 to match the implementation if you choose not to fix the code. | Small (1-2h)
P14 | TRA-008 | WARNING | Spec Conformance / Structural Integrity | Anchor rewrite_links defined but never called — S-06 dead in production | After reassembling translated segments, call `registry.rewrite_links(translated_ast)` before returning the target. Add a verify_output check that every internal `#link` resolves to a heading slug in the target. | Small (2-3h)
P15 | TRA-009 | WARNING | Spec Conformance / Terminological Consistency | Terminology violations classified as WARNING, not BLOCKING | Either escalate terminology violations to BLOCKING at L3+ (stricter than spec, but safer), or document the WARNING classification explicitly in CLAUDE.md and TRA-CONFORMANCE-GUIDE.md. | Small (1h, doc only)
P16 | TRA-010 | WARNING | Spec Conformance / Memory Model | Memory model immutability claims unenforced | Add `model_config = ConfigDict(frozen=True)` to BootstrapConfig. Make AuditTrail.records a tuple or use a frozen list wrapper. Implement or remove count_blocking. | Medium (4-6h)
P17 | TRA-012 | WARNING | Code Quality / Input Sanitization | _sanitize_input bypassed at validate and benchmark boundaries | Move _sanitize_input to a shared utility (e.g., utils.py or a new security.py). Call it at the top of validate_translation, analyze_document, and the benchmark re-verify block. Add a test that confirms bidi-override characters are stripped at every entry point. | Small (2-3h)
P18 | TRA-013 | WARNING | Code Quality / Reproducibility | Audit trail is NOT byte-reproducible (uuid4 + datetime.now) | Make evidence IDs deterministic: `ev_{sha256(content)[:12]}` instead of uuid4. Replace datetime.now(UTC) with a deterministic timestamp derived from the source hash, or accept an optional `timestamp` parameter. Add a test asserting audit-trail byte-equality across two runs of the same input. | Medium (4-6h)
P19 | TRA-014 | WARNING | Security / Path Traversal | No path-traversal protection on config-supplied paths | Resolve all config paths against a project root. Reject paths containing `..` or absolute paths outside the project root. Add a test that confirms a malicious config is rejected. | Small (2-3h)
P20 | TRA-015 | WARNING | Code Quality / Audit Trail | Double audit record on LLM graceful degradation | Add a `return` statement after the degradation-notice audit.append, OR merge the degraded flag into the single normal-path record. Update the test to assert exactly one TRANSLATE_SEGMENT record per segment. | Small (1h)
P21 | TRA-016 | WARNING | Code Quality / Dead Code | AuditTrail.count_blocking is a stub returning 0 unconditionally | Either implement count_blocking by scanning the audit trail for records with 'BLOCKING' in flags_raised, or delete the method and direct readers to reporting.summarize_audit. | Small (30min)
P22 | TRA-017 | WARNING | Code Quality / Dependency Hygiene | 5 unused dependencies inflate install footprint (~50+ transitive packages) | Move litellm to optional-dependencies.llm. Drop pydantic-settings, mdit-py-plugins, structlog, black, pytest-asyncio from the manifest. Add a 'Dependency hygiene' bullet to CLAUDE.md Known gaps. | Small (1-2h)
P23 | TRA-018 | WARNING | Code Quality / Pydantic v2 | Immutability claims on Entity and BootstrapConfig unenforced (no frozen=True) | Add `model_config = ConfigDict(frozen=True)` to Entity, GlossaryEntry, ForbiddenMapping, and BootstrapConfig. For RuntimeContext (which must be mutable), leave unfrozen but document why. Add Field constraints where applicable (e.g., ConformanceLevel enum, non-empty source strings). | Medium (4-6h)
P24 | TRA-019 | WARNING | Code Quality / Assert Usage | 2 runtime asserts in kernel.py stripped under python -O | Replace `assert x is not None` with `if x is None: raise TRAException(...)`. Reserve assert for invariants that are truly impossible to violate. | Small (30min)
P25 | TRA-022 | WARNING | Doc Consistency / Stale Docstring | tra_cli.py docstring says 'Phase 0.1.5 skeleton' with 3 subcommands — file has 4 | Update tra_cli.py:1-7 to list all 4 subcommands (translate, validate, audit, cache-clear) and drop the 'Phase 0.1.5 skeleton' label. | Small (15min, doc only)
P26 | TRA-023 | WARNING | Doc Consistency / Setup Instructions | SKILL.md install instructions omit dev deps — contributor cannot run quality gates | Change SKILL.md:67 to `pip install -e .[dev]` (or `pip install -e '.[dev]'` for zsh). Add a note that the dev extra is required for the quality gates in §7. | Small (15min, doc only)
P27 | TRA-024 | WARNING | Doc Consistency / Implementation Plan | implementation_plan.md Phase 0 all unchecked but fully delivered; file-structure lists nonexistent tests | Either check the Phase 0 boxes (`[x]`) or add a header note 'Phase 0 was delivered before this plan was last updated; checkboxes are stale.' Update the file-structure summary to match the actual test files. | Small (1h, doc only)
P28 | TRA-025 | WARNING | Doc Consistency / Repo Hygiene | No .gitignore at repo root — runtime artifacts (audit_trace.jsonl, cache/, compilation_artifacts/) committed | Add a repo-root .gitignore covering /audit_trace.jsonl, /cache/, /compilation_artifacts/. Run `git rm --cached` on any tracked artifacts. Optionally `rm -rf` the existing root-level artifacts. | Small (30min)
P29 | TRA-026 | WARNING | Doc Consistency / Dead Config | config.yaml cache.expire field parsed by YAML but ignored by code | Either wire cache.expire through to TranslationCache.set (and diskcache's expire parameter), or remove the field from config.yaml and document that the cache has no TTL by design (static facts, per implementation_plan.md §0.4.2). | Small (30min)
P30 | TRA-027 | WARNING | Doc Consistency / Misleading Filename | examples/expected_outputs/security_advisory_zh.L3.md is just translated markdown, not an L3 bundle | Rename to security_advisory_zh.L3.target.md (clarifying it's just the target text). Optionally populate a sibling security_advisory_zh.L3.bundle/ directory with the audit trace + artifacts + conformance verdict, OR add a README explaining the bundle structure. | Small (30min)
P31 | TRA-031 | WARNING | Test Suite / Benchmark Coverage | Only 13 of 24 spec benchmark cases implemented (54%) | Add the 11 missing JSONL cases. Mark S-03 and E-03 as xfail with referenced open issues (TRA-001 and TRA-004 respectively). Document the 13/24 coverage in CLAUDE.md Known gaps. | Medium (4-6h)
P32 | TRA-032 | WARNING | Test Suite / HITL Coverage | HITL only tested for 'accept' path; 'override' and 'skip' untested; interactive=True kernel untested | Parametrize test_hitl_review_decision over ['accept', 'override', 'skip']. Add test_kernel_interactive_mode: construct TRAKernel(config, interactive=True), force an UNRECOVERABLE repair, mock stdin to provide each resolution, assert the target is updated correctly. | Small (2-3h)
P33 | TRA-033 | WARNING | Test Suite / LLM Seam | LLM seam degradation tested for RuntimeError only; other exception types untested | Parametrize the test over [RuntimeError, ValueError, TypeError, OSError, KeyboardInterrupt]. Add tests for llm_translate returning '' and None. | Small (1h)
P34 | TRA-034 | INFO | Test Suite / Quality | conftest.py fixtures used only by test_phase0.py — 10 other test files ignore it | Refactor test_isa.py, test_kernel.py, test_validate.py, test_benchmark.py to use the shared fixtures. Add new fixtures for common patterns (e.g., a minimal source markdown, a fully-built RuntimeContext). | Small (1-2h)
P35 | TRA-035 | INFO | Test Suite / Mutation Coverage | Invariant mutation catch rate: 5 of 12 scenarios (42%) | Close the 3 BLOCKING gaps (TRA-028, TRA-029, TRA-030) to bring the catch rate from 42% to 100% on the critical invariants. Consider adding a CI mutation-testing step (mutmut or cosmic-ray) to prevent future regressions. | N/A (informational)